TASK TABLE for MyRamdam
TEAM GOF

Task	Earliest Start	Length	Type	Dependent On
A – Express Feeling	Week 0	1 Week and 3 Days	Sequential
B – Comment Anonymously	Week 0	1 Week and 2 Days	Parallel
C – Customize Feeling	Week 1	1 Week and 4 Days	Sequential	A
D – Feel Rate	Week 3	2 Weeks	Sequential	C
E – Share Feelings	Week 3	2 Weeks	Sequential	C
F – Edit Comment	Week 1	1 Week and 4 Days	Parallel	B, I
G – Delete Comment	Week 1	1 Week and 4 Days	Parallel	B, I
H – Feeling Report Weekly	Week 3	2 Weeks	Sequential	C
I – Comment Not Anonymously	Week 0	1 Week and 2 Days	Parallel
J – Feeling Report Monthly	Week 3	2 Weeks	Sequential	C
K – Feeling Report Daily	Week 3	2 Weeks	Sequential	C
L - First Full Integration	Week 5	2 Weeks	Sequential	F, G, H, J, K, D, E
M - Final Integration	Week 7	2 Weeks	Sequential	L