69|71
8
Co-F (30)
TC-F &AT-F (20)
UI-F (17)
99|101
13
UI-F/G
116|118
18
TC-G &AT-G (20)
UI-G (17)
Co-G (29)
69|72
9
INTEGRATION (14)
98|101
14
20|22
2
Co-B (29)
49|51
5
142|142
24
TEST AND
CHECK (10)
132|132
23
TC-B &AT-B (20)
INTEGRATION (14)
70|70
10
TC-H &AT-H (20)
Co-H (30)
UI-H (18)
118|118
19
100|100
15
176|176
27
TC-A &AT-A (20)
TC-D &AT-D (20)
FINAL
INTEGRATION (14)
Co-D (27)
115|118
20
70|73
11
Co-B (30)
20|20
3
UI-D (18)
97|100
16
50|50
6
166|166
26
156|156
25
TC-E &AT-E (20)
DEPLOYMENT (10)
Co-E (30)
UI-E (17)
117|118
21
70|71
12
100|101
17
TEST (10)
Legend:
TC – Test Case
Co – Coding
A – Express Feeling
B – Comment Anonymous
C – Customize Feeling
D - “Feel” Rate
E – Share Feeling
F – Edit Comment
G – Delete Comment
H – Feeling reports
UI – User Interface
UI-A (18)
TC-C &AT-C (20)
20|80
4
68|118
22
Co-C (30)
UI-C (18)
Prepared by:
TEAM ORBS
- Apao, Kay
- Bandola, Dareen Mae
- Fuerzas, Cristy Loraine
- Ramos, Jennie
- Sembrano, Angelo
50|100
7
- critical path
0|0
1
INTEGRATION (14)
INTEGRATION (14)
INTEGRATION (14)